## security-analysis
Priority | Category | Issue Title | Description | Current Code Location | Risk Level | Business Impact | Technical Impact | Recommended Solution | Implementation Effort | Timeline
CRITICAL | Security | Hardcoded JWT Secret | JWT secret key is hardcoded as 'your-very-secret-key' in source code | backend/index.js:1 | HIGH | Token forgery attacks could compromise all user sessions | Complete authentication bypass possible | Use environment variables with cryptographically strong random secrets (min 256-bit) | LOW | 1-2 days
CRITICAL | Security | Weak Password Hashing | bcrypt salt rounds set to only 8, below security standards | backend/index.js:67-68 | HIGH | User passwords vulnerable to brute force attacks | Account takeover and data breach | Increase salt rounds to 12+ and enforce strong password policies | LOW | 1 day
CRITICAL | Security | Wide Open CORS Policy | CORS configured to allow all origins with app.use(cors()) | backend/index.js:18 | HIGH | Cross-origin attacks and unauthorized API access | CSRF attacks and data exfiltration | Configure specific allowed origins and headers | LOW | 1 day
CRITICAL | Security | No Input Validation | API endpoints accept raw input without validation or sanitization | Multiple endpoints | HIGH | SQL injection and XSS vulnerabilities | Data corruption and system compromise | Implement schema validation with Joi or express-validator | MEDIUM | 3-5 days
CRITICAL | Security | Error Information Disclosure | Internal error details exposed to clients via err.message | Multiple catch blocks | MEDIUM | System information leakage to attackers | Debugging assistance for malicious actors | Centralized error handling with sanitized responses | MEDIUM | 2-3 days
CRITICAL | Database | Unencrypted SQLite Database | Database file stored without encryption in container | backend/index.js:11 | HIGH | Data exposure if container is compromised | Complete data breach potential | Migrate to PostgreSQL with encryption at rest | HIGH | 1-2 weeks
CRITICAL | Database | No Data Persistence | SQLite file stored in ephemeral container storage | docker-compose.yml | HIGH | Complete data loss on container restart | Business continuity failure | Implement volume mounting and backup strategy | MEDIUM | 2-3 days
CRITICAL | Authentication | Default Credentials | Default admin/creator passwords are predictable and weak | backend/index.js:67-68 | HIGH | Immediate unauthorized access to admin functions | Complete system compromise | Force password change on first login with strong policies | LOW | 1-2 days
HIGH | Security | No Rate Limiting | APIs have no protection against brute force or DDoS attacks | All API endpoints | MEDIUM | Service availability and resource exhaustion | Performance degradation and potential downtime | Implement rate limiting middleware | LOW | 1-2 days
HIGH | Security | No Request Logging | No audit trail or security monitoring in place | Entire application | MEDIUM | Security incidents go undetected | Compliance and forensic analysis impossible | Implement structured logging with Winston | MEDIUM | 2-3 days
HIGH | Authentication | Weak JWT Configuration | JWT tokens may lack proper claims and expiration policies | backend/index.js:248 | MEDIUM | Session management vulnerabilities | Unauthorized access and privilege escalation | Implement proper JWT claims and refresh token strategy | MEDIUM | 3-4 days
HIGH | Container | Root User Execution | Containers running as root user by default | Dockerfile.backend Dockerfile.frontend | MEDIUM | Container escape vulnerabilities | Host system compromise potential | Create non-root user in containers | LOW | 1 day
MEDIUM | Architecture | No API Versioning | APIs lack versioning strategy for backward compatibility | All API routes | LOW | Breaking changes will break existing clients | Integration failures and deployment issues | Implement /api/v1/ versioning pattern | LOW | 1-2 days
MEDIUM | Architecture | Monolithic Structure | All API logic in single 450+ line file | backend/index.js | LOW | Code maintainability and testing complexity | Developer productivity and code quality issues | Refactor into modular structure (routes/ models/ services/) | HIGH | 1-2 weeks
MEDIUM | Operations | No Health Checks | Missing health check endpoints for monitoring | Application infrastructure | LOW | Silent failures and deployment issues | Monitoring and alerting gaps | Add /health and /ready endpoints | LOW | 1 day
MEDIUM | Database | No Migration System | Database schema changes handled manually on startup | backend/index.js:21-127 | MEDIUM | Data loss during schema changes | Development and deployment complexity | Implement proper database migration system | MEDIUM | 3-5 days
LOW | Development | No Testing Strategy | No unit tests integration tests or API tests | Entire codebase | LOW | Regression bugs and deployment confidence | Code quality and reliability issues | Implement comprehensive testing with Jest | HIGH | 1-2 weeks
LOW | Documentation | No API Documentation | Missing Swagger/OpenAPI documentation | API endpoints | LOW | Developer productivity and integration complexity | Onboarding and maintenance overhead | Add Swagger documentation with examples | MEDIUM | 3-5 days
LOW | Code Quality | No Linting Tools | No ESLint Prettier or code quality enforcement | Development workflow | LOW | Code consistency and quality degradation | Technical debt accumulation | Add ESLint Prettier and pre-commit hooks | LOW | 1-2 days
LOW | Operations | No CI/CD Pipeline | Manual deployment process without automation | Development workflow | LOW | Human errors and deployment inconsistencies | Release velocity and reliability issues | Implement GitHub Actions for automated pipeline | MEDIUM | 1 week